## planejamento
		0	1	2	3	4	5	6	7	8	9	10					1	2	3	4	5	6	7	8	9	10
			15/07/22	16/07/22	17/07/22	18/07/22	19/07/22	20/07/22	21/07/22	22/07/22	23/07/22	24/07/22					15/07/22	16/07/22	17/07/22	18/07/22	19/07/22	20/07/22	21/07/22	22/07/22	23/07/22	24/07/22
			6	7	1	2	3	4	5	6	7	1					6	7	1	2	3	4	5	6	7	1
1	PLANEJAMENTO													1	PLANEJAMENTO
	_ler case		2												_ler case		2
	_definir atividades		3												_definir atividades		3
	_construir burndown			1											_construir burndown			1
	_definir arquitetura de software														_definir arquitetura de software
2	BANCO DE DADOS													2	BANCO DE DADOS
	_definir as entidades			2											_definir as entidades			2
	_desenhar diagrama ER			2											_desenhar diagrama ER			2
	_desenvolver script SQL: construir DB e popular			3											_desenvolver script SQL: construir DB e popular			3
3	DESENVOLVIMENTO													3	DESENVOLVIMENTO
	_iniciar aplicação			2											_iniciar aplicação			2
	_endpoint POST wallet/ buy				5										_endpoint POST wallet/ buy						3	2
	_endpoint POST wallet/ sell				5										_endpoint POST wallet/ sell						3	2
	_endpoint GET BY CLIENT assets/ {id-client}					5									_endpoint GET BY CLIENT assets/ {id-client}						4	1
	_endpoint GET BY ASSET assets/ {id-asset}					5									_endpoint GET BY ASSET assets/ {id-asset}					5
	_endpoint POST account/ deposit						5								_endpoint POST account/ deposit				5
	_endpoint POST account/ withdraw						5								_endpoint POST account/ withdraw				3	2
	_endpoint GET account/ {id-client}							5							_endpoint GET account/ {id-client}				5
4	TESTES							5	10					4	JWT								5
5	ENTREGA													5	ENTREGA
	_documentação									5					_documentação									5	5	5
	_deploy da API									5
	_swagger										5				_swagger										10
		80	75	65	55	45	35	25	15	5	0	0				80	75	65	52	45	35	30	25	20	5	0

	GRÁFICO BURNDOWN PARA PROJETO INVEXP

		dias de projeto